## KW50, 2025
# | Region | Type | Project/ Product | Commodity | Parent PF Code | SWAT ID / Bundle ID | Part Description | PN | Recommended Supplier (s) | Presenter | Decision Level | Peak Year Spend | LT Spend | Comment | Sourcing Decision | Notes/Task/ Resp./ Due Date | CQA PC PRICE | Rec. Supplier Landed | Average Volume | LT volume | Average Year Saving vs CQA | LT saving | CQA Tooling | Rec. Supplier Tooling | Tooling Saving vs CQA
1 | AP | New | JAC X2411 | EL | EL02002 ECU Build to Spec | B/2025/00304 110000238204 | ECU ACTIVE-CONTROLLED-RETRACTOR | R002H159A | DIAS Automotive Electronic Systems | Melisa Bouzo | L2 | 9.6 Mio RMB 1.2 Mio Euro | 55 Mio RMB 6,95 Mio Euro | supplier full responsible for parts build to spec | Approved | 1. To check with supplier about NQC survey completion to avoid having sustainablity score 0. -- CM Melisa | 72,03 RMB/pc 9,12 Euro/pc | 67,52 RMB/pc 8,55 Euro/pc | 135600 | 813600 | -77292 | -463752 | 0 | 195,600 RMB 24666 Euro | 24666
|  |  | Changan E518/F61 |  |  | B/2025/00304 110000032038 |  | R003D871A |  |  |  | 4,4 Mio RMB 552K Euro | 20,3 Mio RMB 2,6 Mio Euro |  |  |  | 72,00 RMB/pc 9,11 Euro/pc | 69,52 RMB/pc 8,8 Euro/pc | 48667 | 292000 | -15086.77 | -90520 | 0 | 1,150,400 RMB 145,620 Euro | 145620
2 | NA | CARRY OVER | SPR6 NCAR,R2, T1 SUV, T2 SUV | TUBES | SC02002 | 110000032122 | TUBE, RETRACTOR PRETENSION | A028R629A | Tianjin Jinrong | Violeta Beltran del Rio | L2 | 1,1 M USD 1,0 Mio Euro | 7,7 M USD 7.0 M Euro | 1st case to build MX local production line for SPR6.1 tube. | Approved | 1. Tool cost above CQA. To double check with Jinrong for the tool cost, 2nd tool should be cheaper than 1st tool. -- CM Violeta 2. To share the 3 different Jinrong offer scenarios with Rivian and BMW sales, to double check about our USMCA commitment with customer, to further decide the final option based on USMCA needes. -- PP Mario 3. To validate all RMs. -- Product Mgr T. Rossman to follow up with ZF Lifetec engineering. 4. Jinrong readiness: IATF planned, and to pass ZF Lifetec audit within 2026, to support the PPAP.-- ZF Lifetec SDE NA. 5. To check available NA coaters and share coater contacts (e.g. bright finishing) with Jinrong, to further improve the cost. Or to check with Jinrong the possibility to do coating in house. -- CM | 0,8459 USD/pc 0,769 Euro/pc | 0,80488 USD/pc 0,73171 Euro/pc | 1068308 | 9614770 | -39837.2053 | -358534.7733 | 0 | 109717 USD 99743 Euro | 99743

## Scorecard
1. DIAS | 62
2. Jinrong | 91

## BPP
1. DIAS | 0
2. Jinrong | 122641