## KW05, 2026
# | Region | Type | Project/ Product | Commodity | Parent PF Code | SWAT ID / Bundle ID | Part Description | PN | Recommended Supplier (s) | Presenter | Decision Level | Peak Year Spend | LT Spend | Comment | Sourcing Decision | Notes/Task/ Resp./ Due Date | CQA PC PRICE | Rec. Supplier Landed | Average Volume | LT volume | Average Year Saving vs CQA | LT saving | CQA Tooling | Rec. Supplier Tooling | Tooling Saving vs CQA
1 | NA | GCS | GM T1XX-2 PU | CH01 | CH01016 | 110000221367 B/2025/00293 | CAGE | 34271488B | Wilko Plastics | Alba Guerra | L2 | 290K USD 1.9Mio Euro | 1.9 Mio USD 1.7 Mio Euro | 1. 'Current supplier ACE (AP), resourcing for NA 2. Prices based on different cavitation: ACE 4 cav, Wilko 8 cav, Prism 8 cav. 3. Prism: recent concern of not keeping the committed time. | To follow up offline | 1. Wilko Timing: 20 weeks for FOT, 28 weeks for PPAP. to plan a timing for re-validation -- PM Pradeep So far we are covering with ACE parts. Additional customer approval will be needed. 2. To check if tooling will be paid with lumpsum or with amortization. -- PP Mario 3. To present this case to CCB to get CCB2 approval.-- PP Mario 4. To try to re-negotiate with Prism, to see if they can achieve a better cost, to understand the gap between Wilko and Prism, as both are based on 8 cav. -- CM Alba. | 0,132 USD/pc 0,165 EUR/pc | 0,1034 USD/pc 0,09587 EUR/pc | 1977649 | 17798840 | -56560.7614 | -509046.824 | 157330 Euro 147025 USD | 157330 Euro 147025 USD | 0
|  |  | GM C1UC/UL - 2 |  |  | 110000221430 B/2025/00293 | CAGE | 34324310A | Wilko Plastics | Alba Guerra | L2 | 331K USD 301K Euro | 2,2 Mio USD 2 Mio Euro |  |  |  | 0,150 USD/pc 0,1363 EUR/pc | 0,1041 USD/pc 0,0946 EUR/pc | 2303500 | 20731503 | -105730.65 | -951575.9877 | 157330 Euro 147025 USD | 157330 Euro 147025 USD | 0
2 | NA | GCS | SPR8 | SC06 | SC06005 Cut&Bend¦Washers&Discs¦Passenger Cars | 110000030956 | BEARING | 34192429B | Engineering Specialties, Inc. | Wendy Li | L3 | 229K Euro | 805K Euro | 1. CCB2 approved 2. All NA volume will be moved to ESI. 3. USMCA compliance: ESI will produce it out of NA, not just as a dealer. 4. CM Strategy: This bearing or washer is not typical stamping part, need to keep ESI for such parts. | Approved | 1. ESI 20-24 weeks for FOT, tooling activities started Nov 2025 | 0,083 EUR/pc | 0,0561 EUR/pc | 3957195 | 15828781 | -106448.5455 | -425794.2089 | 0 | 44455 Euro | 44455