## KW39, 2026
# | Region | Type | Project/ Product | Commodity | Parent PF Code | SWAT ID / Bundle ID | Part Description | PN | Recommended Supplier (s) | Presenter | Decision Level | Peak Year Spend Euro | LT Spend Euro | Comment | Sourcing Decision | Notes/Task/ Resp./ Due Date | CQA PC PRICE | Rec. Supplier Landed | Average Volume | LT volume | Average Year Saving vs CQA | LT saving | CQA Tooling | Rec. Supplier Tooling | Tooling Saving vs CQA
1 | EU, NA | New | MBEAL | CH01 | CH01016 Medium Precision | B/2025/00361 110000034017 | ECU Housing, WMS | R003B136A | Ningbo Deke Precision MoldingCo., L | Sandra Novegil | L2 | 439K Euro | 2,5Mio Euro | 1. CN volume not yet nomincated by MB 2. globally only 277K Euro tooling budget for ECU Housing and cover 3. TR closed with Deke 4. ECU PV needed May 2026, needs to have ECU housing and cover provided to EMS supplier few weeks ahead to support PV build. 5. CQA based on different design and volume. | Approved with conditions | 1. To check with engineering and SDE about cleanliness requirement, benchmarking with Staamp current pratice: cleanliness tested once per year, combining the comment of CE, if high-end cleaning or cleaning process ever really needed. --BUP Rafal, Deke to seperate the cleanling cost in QAF to show reduction potential. --SP Sandra 2. To continue the packaging cost improvement 1) to check and access with Kimball if their process allow us to pack ECU housing and cover together --BUP Rafal, SP Melisa 2) to check with Engineering and SDE if bulk package for cover can be approved instead of blister 3. To kickoff tooling at Deke-- TEAM 4. To close the gap towards CQA, to list down all the gap closure activities and to follow up bi-weekly, to define task owner, list to be distributed KW40--BUP Rafal, SP Sandra with ECU team 5. To request BP lumpsum from Deke for 2026.--SP Sandra | 0,64 Euro/pc | 0,74 Euro/pc | 378979 | 3410814 | 37897.9 | 341081.4 | 277000 | 4352 | -272648
|  | New | MBEAL | CH01 | CH01016 Medium Precision | B/2025/00361 110000034018 | ECU Housing, w/o WMS | R003H147A |  |  |  | 139K Euro | 873K Euro |  |  |  | 0,64 Euro/pc | 0,66 Euro/pc | 165280 | 1322241 | 4958.4 | 39667.23 | 0 | 138908 | 138908
|  | New | MBEAL | CH01 | CH01016 Medium Precision | B/2025/00361 110000034019 | ECU Cover | R004D369A |  |  |  | 139K Euro | 852K Euro |  |  |  | 0,12 Euro/pc | 0,18 Euro/pc | 525895 | 4733055 | 31553.7 | 283983.3 | 0 | 49529 | 49529
2 | AP | New | MBEAL | CA04 | CA04003 High complexity parts | 110000035117 | Locking Disc Alu | R003H729B | Shenzhen XLX | Jordan ZHAO | L4 | 10K Euro | 61K Euro Euro | 1. Tooling cost will be paid in lump sum, with approved CEA, tool owner ZF LIFETEC. 2. No TR&R cost included in the pc price. In case there will be new projects for carry over sourcing, new tooling cost needs to be considered in Business Case. 3. CQA RM index is Yr2025 Q2, and the awarded RM index is Yr2026 Q2. 4. Double check whether BPG is including CNC machining process.---Sep.21st @Jordan Zhao CHN ROSMF 5. If the yearly volume could meet 1M or 2M/year, Strategy Procurement can help with further negotiation to meet lower cost. | Approved offline KW38 |  | 0,2108 Euro/pc 1,75 RMB/pc (Q2/25 RM index) | 1) 1,8317 RMB/pc (Q2/25 RM index) 2) 1,90 RMB/pc (Q2/26 RM index) | 28163 | 253464 | 2300.9171 | 20708.0088 | 39,157 Euro 325.000 RMB | 37750 Euro 286.000 RMB | -4699.1687
3 | AP | New | MBEAL Family8.S | SC02 | SC02002 Formed Tubes | 110000034871 | SPR8.S (E) TUBE | R003D867A | Huzhou Iron Force Metal ProductsCo. | Haojie Ding | L4 | 99K Euro 782K RMB | 585K Euro 4.6Mio RMB | 1. Allocation into MB.EAL lifecycle volume 880,174 pcs 2. Approved by Family 8.SE | Approved offline KW38 |  | 0.6709 Euro/pc 5.3 RMB/pc | 0.6646 Euro/pc 5.25 RMB/pc | 88017 | 880174 | -554.5071 | -5545.0962 | 107595 Euro 850000 RMB | 101266Euro 850000 RMB | 0
4 | EU | New | MBEAL | SC06 | SC06003 | 110000035048 | Retractor Bracket | R004C217A | Advanced Moulding Production Ltd. | Lingqin Hu | L4 | 25K Euro | 149K Euro | 1. brackets with welded nut 2. 400T, 2 Cavity, LH RH | Approved offline KW39 | 1. Comment about tooling cavities to be updated in QAF and in capa. --SP Tracy, KW39 | 0,60 Euro/pc | 0,4810 Euro/pc | 34459 | 310127 | -4100.621 | -36905.113 | 140000 | 36308 | -103692
5 | EU | New | MBEAL | SC06 | SC06003 | 110000035049 | Retractor Bracket | R004C216A | Advanced Moulding Production Ltd. | Lingqin Hu | L4 | 25K Euro | 149K Euro |  | Approved offline KW39 |  | 0,60 Euro/pc | 0,4810 Euro/pc | 34459 | 310127 | -4100.621 | -36905.113
7 | EU | New part | 2028 MBEAL SBS | Electromechanicals | EA03011 | B/2026/00135 | RNS5s Mechanical Diagnosable Resistor Coded Switch wire assembly | R004F937 | ODW-ELEKTRIK | Cesar Espinoza | L2 | 677K Euro | 4,07 Mio Euro | 1. ODW, so far globally the only developed supplier who can deliver NORC switches. AP team working on developing a 2nd source. TR ongoing. 2. ODW PT 90days, consignment available | Offline reviewed KW38, Rejected, To be followed up | 1. To add the 2 NA SWAT cases for PN R004G206 and R004J281 into the bundle. -- SP Cesar, CW39 2. To add a NPV comparison incoterm supplier FCA condition vs CQA FCA condition. -- SP Cesar, CW39 3. To check with AP team regarding mechanical switch localization status/timing plan. 4 years' lead time until SOP too long. Comparison with AP source consider AP price w/wo line amortization. -- SP Cesar, BUP Zhi 3. To negotiate the prices, 1. to have recommended supplier NPV meeting CQA NPV, (both under FCA condition), 2. then to maximize LTA and BPP saving, to work out a best saving solution meeting CQA. -- SP Cesar 4. To have GAP analysis, to request CE involvement in negotiation with ODW, meeting to be planned KW40. -- SP Cesar, CE Raymond. 5. MBEAL SUV further new sourcing would start in Sept. with lifetime volume 3 Mio. pcs. To further negotiate lower price for whole MBEAL EU&NA package.--BUP Zhi, Agustin | 1.6 | 1.5833 | 8794 | 79147 | -415.0768 | -3735.7384 | 0 | 0 | 0
[8 empty] | R004F938 | [8 empty] | 1.6 | 1.5282 | 8794 | 79146 | -898.7468 | -8088.7212 | 0 | 0 | 0
[8 empty] | R004H057 | [8 empty] | 1.55 | 1.5934 | 48350 | 435150 | 618.88 | 5569.92 | 0 | 0 | 0
[8 empty] | R004H268 | [8 empty] | 1.55 | 1.5383 | 50763 | 456865 | -2137.1223 | -19234.0165 | 0 | 0 | 0
[8 empty] | R004G206 | [8 empty] | 1 | 1.4195 | 111179 | 1000613 | 44304.8315 | 398744.2805 | 0 | 0 | 0
[8 empty] | R004J281 | [8 empty] | 1.7 | 2.0134 | 25042 | 225375 | 7319.7766 | 65877.1125 | 0 | 0 | 0
[8 empty] | R004J284 | [8 empty] | 2.1 | 2.1071 | 10966 | 98695 | -130.4954 | -1174.4705 | 0 | 0 | 0
[8 empty] | R004J285 | [8 empty] | 2.1 | 2.0521 | 10966 | 98695 | -733.6254 | -6602.6955 | 0 | 0 | 0
| NA | New part | 2029 MBEAL SBS | Electromechanicals | EA03011 | 110000035182 |  | R004G206 | ODW-ELEKTRIK | [7 empty] | 1 | 1.4195 | 341383 | 2731062 | 136041.1255 | 1088328.207 | 0 | 0 | 0
| NA | New part | 2029 MBEAL SBS | Electromechanicals | EA03011 | 110000035195 |  | R004J281 | ODW-ELEKTRIK | [7 empty] | 1.7 | 2.0134 | 13212 | 105692 | 3861.8676 | 30893.7716 | 0 | 0 | 0